## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project (Intoduction to AI, ML and GPT) | MUST HAVE | No Dependency | Shruti Jaiswal | 3- Completed
S1 | S1 | US-001 | Workflow Creation and fixing Project Deadlines | MUST HAVE | No Dependency | Shruti Jaiswal | 3- Completed
S1 | S1 | US-001 | Document Discussion (Agile Template) | MUST HAVE | Excel | Shruti Jaiswal | 3- Completed
S1 | S1 | US-001 | Use Case Reasearch and Preparation | SHOULD HAVE | kommunicate.io | Shruti Jaiswal | 3- Completed
S2 | S2 | US-001 | Learning Python (loops, Functions, OOPs, Exception Handling) | MUST HAVE | Google Meet (Mentor) | Shruti Jaiswal | 3- Completed
S3 | S3 | US-001 | Learning Natural Language Processing (Aquisation,Preprocessing,Feature Engineering,Modelling) | MUST HAVE | Google Meet (Mentor) | Shruti Jaiswal | 3- Completed
S4 | S4 | US-001 | Learning Flask (Revising HTML, CSS,JS) and Structured Query Language (Sqlite) | SHOULD HAVE | Google Meet (Mentor) | Shruti Jaiswal | 3- Completed
S5 | S5 | US-001 | Project Discussion Module 1 (Choosing Dataset and Preprocessing) | MUST HAVE | Using PDF | Shruti Jaiswal | 3- Completed
S6 | S6 | US-001 | Project Discussion Module 2 (Model Selection and Training) | MUST HAVE | VS Code and Jupyter Notebook | Shruti Jaiswal | 3- Completed
S7 | S7 | US-001 | Project Discussion Module 3 (Frontend Debelopment) | MUST HAVE | Streamlit | Shruti Jaiswal | 3- Completed
S8 | S8 | US-001 | Project Discussion Module 4 (Intergration,Testing and Deployment) | SHOULD HAVE | Yet to be decided | Shruti Jaiswal | 2- In Progress
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 105 | 22 | 19 | 15 | 14 | 14 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to project (Intoduction to AI, ML and GPT) | 2024-12-04 | 2024-12-05 | Shruti | Others | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-02 | Workflow Creation and fixing Project Deadlines | 2024-12-06 | 2024-12-08 | Shruti | Design | 3- Completed | 9 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-03 | Document Discussion (Agile Template) | 2024-12-09 | 2024-12-09 | Shruti | Others | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-04 | Use Case Reasearch and Preparation | 2024-12-10 | 2024-12-10 | Shruti | Others | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-05 | Learning Python (loops, Functions, OOPs, Exception Handling) | 2024-12-11 | 2024-12-17 | Shruti | Others | 3- Completed | 12 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-06 | Learning Natural Language Processing (Aquisation,Preprocessing,Feature Engineering,Modelling) | 2024-12-18 | 2024-12-24 | Shruti | Others | 3- Completed | 12 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-07 | Learning Flask (Revising HTML, CSS,JS) and Structured Query Language (Sqlite) | 2024-12-25 | 2025-01-31 | Shruti | Others | 3- Completed | 12 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-08 | Project Discussion Module 1 (Choosing Dataset and Preprocessing) | 2025-01-01 | 2025-01-07 | Shruti | Others | 3- Completed | 12 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-09 | Project Discussion Module 2 (Model Selection and Training) | 2025-01-08 | 2025-01-14 | Shruti | Build | 3- Completed | 12 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-10 | Project Discussion Module 3 (Frontend Debelopment) | 2025-01-15 | 2025-01-21 | Shruti | Coding | 3- Completed | 12 | 2 | 1 | 2 | 2 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-11 | Project Discussion Module 4 (Intergration,Testing and Deployment) | 2025-01-22 | 2025-01-28 | Shruti | Integration Test | 2- In Progress | 12 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Ambiguity regarding project timelines and deliverable expectations. | Conducted a meeting with the mentor to establish clear timelines and deliverable expectations..
Sprint 2 | Day 11 | Limited understanding of advanced programming concepts such as polymorphism and exception handling. | Attended a detailed session with the mentor to enhance understanding of polymorphism and exception handling.
Sprint 3 | Day 20 | Challenges in effectively applying feature engineering techniques, particularly TF-IDF. | Sought clarification and practical examples from the mentor to effectively apply TF-IDF in feature engineering.
Sprint 4 | Day 27 | Insufficient knowledge about configuring and managing virtual environments. | Collaborated with the mentor to configure a virtual environment and understand best practices for its management.
Sprint 5 | Day 31 | Difficulties in identifying, collecting, and leveraging appropriate datasets for the project. | Conducted research and consulted the mentor to identify, collect, and utilize appropriate datasets for the project..
Sprint 6 | Day 38 | Uncertainty in model selection and the methodology for performance evaluation. | Performed additional research and conducted comparative analysis to evaluate model accuracy and relevance..
Sprint 7 | Day 46 | Inadequate understanding of route handling and implementation within the Flask framework. | Reviewed online resources and sought guidance from the mentor to efficiently implement routes in Flask.
Sprint 8 | Day 55 | Requirement for constructive feedback to refine project deliverables and finalize outcomes. | Presented the project to the mentor, incorporating their feedback to refine deliverables and address final improvements.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-12-04 | 2024-12-10 | Shruti Jaiswal | Conduct research on project workflow and development. | Making assumptions about project requirements. | Finalizing project deadlines and maintaining agile documentation. | Scheduled a meeting with the team and mentor for project discussions.
2 | Sprint 2 | 2024-12-11 | 2024-12-17 | Shruti Jaiswal | Learn fundamental Python concepts. | Engaging in redundant workflow creation. | Practicing Python through structured exercises. | Completed assignments on time as per the mentor's guidance.
3 | Sprint 3 | 2024-12-18 | 2024-12-24 | Shruti Jaiswal | Study Natural Language Processing (NLP). | Revisiting fundamental Python concepts. | Advancing NLP learning with practical applications. | Developed minor projects to reinforce NLP concepts.
4 | Sprint 4 | 2024-12-25 | 2024-12-31 | Shruti Jaiswal | Gain proficiency in Flask and SQL. | Relearning Natural Language Processing basics. | Practicing SQLite database management. | Built a simple Flask-based application integrated with SQLite.
5 | Sprint 5 | 2025-01-01 | 2025-01-07 | Shruti Jaiswal | Acquire relevant datasets for model training. | Relearning Flask and SQL without practical application. | Searching for suitable datasets. | Conducted extensive dataset searches across multiple sources.
6 | Sprint 6 | 2025-01-08 | 2025-01-14 | Shruti Jaiswal | Research and train various machine learning models. | Conducting unstructured searches for datasets. | Selecting and refining machine learning models. | Tested and compared the accuracy of various machine learning models.
7 | Sprint 7 | 2025-01-15 | 2025-01-21 | Shruti Jaiswal | Develop the frontend interface. | Searching for models without analysis. | Enhancing the frontend with additional features. | Designed and deployed a dynamic website for the model.
8 | Sprint 8 | 2025-01-22 | 2025-01-28 | Shruti Jaiswal | Implement integration, testing, and deployment strategies | Designing the frontend without implementation. | Integrating the frontend, model, and database while performing rigorous testing. | Conducted scenario-based testing by defining and executing test cases.